## Sheet1
| Project | Summary | System / Product | Number | State | Assigned To | Detected By | Severity | Priority | Target Close Date | Created | Detected On | Updated
Assigned To: (empty) (1)
| Improved UI | Fields need to read headings and subheadings | Make a Claim | DEF0003933 | Re-Open |  | Gillian | Severity 2 | Priority 2 |  | 2016-06-16 13:05 | 2016-06-16 12:57 | 2016-06-29 09:11
Assigned To: Adriana (1)
| Improved Sign Up/On | Not able to complete registration |  | DEF0004065 | Open | Adriana | Kiran | Severity 2 | Priority 2 |  | 2016-06-23 10:37 | 2016-06-23 10:29 | 2016-06-27 11:08
Assigned To: Anthony (2)
| Improved Sign Up/On | Session expiry message is not displayed |  | DEF0003719 | Re-Open | Anthony | Kiran | Severity 2 | Priority 2 |  | 2016-06-07 13:35 | 2016-06-07 13:29 | 2016-06-27 13:51
| Improved UI | Coverage descriptions are not displaying for all coverages | Business | DEF0004010 | Open | Anthony | Lisa | Severity 2 | Priority 2 |  | 2016-06-21 13:05 | 2016-06-21 11:51 | 2016-06-27 14:13
Assigned To: Attila (4)
| Improved UI | Buttons need to be more descriptive | Make a Payment | DEF0004079 | Open | Attila | Gillian | Severity 2 | Priority 2 |  | 2016-06-23 12:26 | 2016-06-23 12:20 | 2016-06-23 14:28
| Improved Sign Up/On | Not able to toggle check box using keyboard |  | DEF0004106 | Open | Attila | Kiran | Severity 2 | Priority 2 |  | 2016-06-25 07:11 | 2016-06-25 07:10 | 2016-06-27 08:21
| Improved UI | Need to read format | Make a Payment | DEF0004112 | Pending Mgt Decision | Attila | Gillian | Severity 2 | Priority 2 |  | 2016-06-25 09:19 | 2016-06-25 09:17 | 2016-06-29 08:47
| Improved UI | title is not read | Make a Claim | DEF0004144 | Open | Attila | Gillian | Severity 2 | Priority 2 |  | 2016-06-29 09:23 | 2016-06-29 09:19 | 2016-06-29 09:23
Assigned To: Claudiu (5)
| Improved UI | Drop down fields are selected twice. | Business | DEF0003412 | Open | Claudiu | Gillian | Severity 2 | Priority 2 |  | 2016-05-24 15:57 | 2016-05-24 15:53 | 2016-06-21 10:29
| Improved UI | Continue buttons read incorrectly using screen reader | Make a Payment | DEF0003445 | Monitor | Claudiu | Gillian | Severity 2 | Priority 2 |  | 2016-05-25 12:26 | 2016-05-25 11:47 | 2016-06-28 10:00
| Improved UI | Edit buttons not read correctly using screen reader | Make a Payment | DEF0003447 | Open | Claudiu | Gillian | Severity 2 | Priority 2 |  | 2016-05-25 12:33 | 2016-05-25 12:28 | 2016-06-28 10:00
| Improved UI | Fields with Examples are being read as prepopulated | Make a Claim | DEF0004089 | Pending Mgt Decision | Claudiu | Gillian | Severity 2 | Priority 2 |  | 2016-06-23 14:27 | 2016-06-23 14:14 | 2016-06-29 08:52
| Improved UI | Fields are being read with "auto complete" |  | DEF0004115 | Pending Mgt Decision | Claudiu | Gillian | Severity 2 | Priority 2 |  | 2016-06-25 10:50 | 2016-06-25 10:49 | 2016-06-28 14:31
Assigned To: Devaraj (1)
| Improved Sign Up/On | cookie expiry message displayed if left ideal for few hours and login |  | DEF0004014 | Need More Information | Devaraj | Devaraj | Severity 2 | Priority 2 |  | 2016-06-21 13:58 | 2016-06-21 13:54 | 2016-06-25 19:40
Assigned To: Gillian (2)
| Improved UI | Table column title should be Limite not Montant as it is now | Farm | DEF0002168 | Monitor | Gillian | Sarah | Severity 2 | Priority 2 |  | 2016-04-19 12:06 | 2016-04-19 12:02 | 2016-06-02 09:45
| Improved UI | Financial Advisor is Incorrect | Business | DEF0002614 | Monitor | Gillian | Gillian | Severity 2 | Priority 2 |  | 2016-04-28 12:52 | 2016-04-28 12:46 | 2016-06-13 11:45
Assigned To: Joseph (4)
| Improved Sign Up/On | Login session not expired if page is not in opened state |  | DEF0003715 | Re-Open | Joseph | Kiran | Severity 2 | Priority 2 |  | 2016-06-07 12:44 | 2016-06-07 12:40 | 2016-06-28 15:56
| Improved UI | When tabbing to field the whole form is read | Make a Claim | DEF0004038 | Re-Open | Joseph | Gillian | Severity 2 | Priority 2 |  | 2016-06-22 14:43 | 2016-06-22 14:41 | 2016-06-28 14:35
| Improved UI | Screen reader begins in middle of page | Make a Claim | DEF0004130 | Open | Joseph | Gillian | Severity 2 | Priority 2 |  | 2016-06-28 11:33 | 2016-06-28 11:30 | 2016-06-28 14:43
| Improved UI | Print and Make another payment buttons do not work with enter/return button | Make a Payment | DEF0004131 | Open | Joseph | Gillian | Severity 2 | Priority 2 |  | 2016-06-28 11:54 | 2016-06-28 11:53 | 2016-06-28 15:50
Assigned To: Kiran (1)
| Improved Sign Up/On | Technical error during 'Resend validation' |  | DEF0004099 | Monitor | Kiran | Kiran | Severity 2 | Priority 2 |  | 2016-06-24 09:25 | 2016-06-24 09:22 | 2016-06-24 10:30
Assigned To: Lisa (8)
| Improved UI | Building Description does not appear on UI for Coverages or Endorsements | Business | DEF0002657 | Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-04-29 08:52 | 2016-04-29 08:47 | 2016-06-08 10:58
| Improved UI | Equipment Endorsement Label Does Not Appear on UI | Business | DEF0002662 | Re-Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-04-29 10:15 | 2016-04-29 10:02 | 2016-06-15 10:46
| Improved UI | Fine Art Coverages Label Does Not Appear on UI | Business | DEF0002674 | Re-Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-04-29 12:01 | 2016-04-29 12:01 | 2016-05-05 15:37
| Improved UI | Sign Coverages Label Does Not Appear on UI | Business | DEF0002681 | Re-Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-04-29 13:07 | 2016-04-29 13:07 | 2016-05-05 15:41
| Improved UI | Contractors Equipment Label Does Not Appear on UI | Business | DEF0002683 | Re-Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-04-29 14:11 | 2016-04-29 14:11 | 2016-06-08 10:29
| Improved UI | Waiver of Subrogation (Landlord) Endorsement does not appear on UI | Business | DEF0002872 | Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-05-04 12:49 | 2016-05-04 12:46 | 2016-06-15 11:42
| Improved UI | Wrap Up Coverages Not Loaded | Business | DEF0002928 | Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-05-05 14:44 | 2016-05-05 14:44 | 2016-05-05 15:55
| Improved UI | Builder's Risk Coverage Names have not been loaded | Business | DEF0002930 | Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-05-05 14:47 | 2016-05-05 14:47 | 2016-05-05 15:56
Assigned To: Sarah (1)
| Improved UI | Missing My Financial Advisor Data | Farm | DEF0002099 | Monitor | Sarah | Sarah | Severity 2 | Priority 2 |  | 2016-04-18 12:50 | 2016-04-18 12:45 | 2016-05-25 14:30
Assigned To: Scott (3)
| Improved Sign Up/On | Password rules not validating in Advisor setup |  | DEF0003513 | Re-Open | Scott | Kiran | Severity 2 | Priority 2 |  | 2016-05-31 13:07 | 2016-05-31 13:04 | 2016-06-28 09:08
| Improved Sign Up/On | Wrong error message displayed when user enter wrong password more than three times during email upd |  | DEF0004007 | Re-Open | Scott | Kiran | Severity 2 | Priority 2 |  | 2016-06-21 11:08 | 2016-06-21 11:05 | 2016-06-29 09:35
| Improved Sign Up/On | default focus is not set in Register, Forgot email/password screens |  | DEF0004142 | Open | Scott | Kiran | Severity 2 | Priority 2 |  | 2016-06-28 16:34 | 2016-06-28 16:33 | 2016-06-29 08:56
Assigned To: Subra (1)
| Improved Sign Up/On | Policy does not display |  | DEF0003670 | Re-Open | Subra | Sue Try | Severity 2 | Priority 2 |  | 2016-06-06 12:46 | 2016-06-06 12:39 | 2016-06-14 09:41
Assigned To: Timothy (3)
| Improved Sign Up/On | Headrs does not look correct for all English emails |  | DEF0002160 | Re-Open | Timothy | Devaraj | Severity 2 | Priority 2 |  | 2016-04-19 11:07 | 2016-04-19 11:03 | 2016-06-23 14:36
| Improved UI | Email Confirmation Missing graphic | Make a Payment | DEF0003317 | Open | Timothy | Sarah | Severity 2 | Priority 2 |  | 2016-05-18 14:41 | 2016-05-18 14:34 | 2016-06-20 15:53
| Improved Sign Up/On | Session expiry message buttons has wrong names. |  | DEF0004138 | Open | Timothy | Kiran | Severity 2 | Priority 2 |  | 2016-06-28 15:09 | 2016-06-28 15:06 | 2016-06-28 15:09
Assigned To: Vandy (5)
| Improved Sign Up/On | Wrong success message displayed when migrating user changed the email id. |  | DEF0003912 | Re-Open | Vandy | Kiran | Severity 2 | Priority 2 |  | 2016-06-15 11:21 | 2016-06-15 11:13 | 2016-06-27 16:23
| Improved UI | Screen reader should start at the top of the page | Make a Claim | DEF0004083 | Pending Mgt Decision | Vandy | Gillian | Severity 2 | Priority 2 |  | 2016-06-23 13:47 | 2016-06-23 13:24 | 2016-06-28 11:09
| Improved Sign Up/On | Success message needed for the scenario when user validates login email id |  | DEF0004136 | Open | Vandy | Kiran | Severity 2 | Priority 2 |  | 2016-06-28 15:01 | 2016-06-28 14:58 | 2016-06-28 15:01
| Improved Sign Up/On | We need new subject line the the emails user receive when user update anything in My Profi |  | DEF0004137 | Open | Vandy | Kiran | Severity 2 | Priority 2 |  | 2016-06-28 15:03 | 2016-06-28 15:01 | 2016-06-28 15:03
| Improved Sign Up/On | Account locked message not displayed |  | DEF0004140 | Open | Vandy | Kiran | Severity 2 | Priority 2 |  | 2016-06-28 16:24 | 2016-06-28 16:18 | 2016-06-28 16:24