## Sheet1
| Project | Summary | System / Product | Number | State | Assigned To | Detected By | Severity | Priority | Target Close Date | Created | Detected On | Updated
Assigned To: Adriana (1)
| Improved Sign Up/On | Not able to complete registration |  | DEF0004065 | Open | Adriana | Kiran | Severity 2 | Priority 2 |  | 2016-06-23 10:37 | 2016-06-23 10:29 | 2016-06-27 11:08
Assigned To: Anthony (2)
| Improved Sign Up/On | Session expiry message is not displayed |  | DEF0003719 | Re-Open | Anthony | Kiran | Severity 2 | Priority 2 |  | 2016-06-07 13:35 | 2016-06-07 13:29 | 2016-06-27 13:51
| Improved UI | Coverage descriptions are not displaying for all coverages | Business | DEF0004010 | Open | Anthony | Lisa | Severity 2 | Priority 2 |  | 2016-06-21 13:05 | 2016-06-21 11:51 | 2016-06-27 14:13
Assigned To: Attila (11)
| Improved UI | Fields need to read headings and subheadings | Make a Claim | DEF0003933 | Open | Attila | Gillian | Severity 2 | Priority 2 |  | 2016-06-16 13:05 | 2016-06-16 12:57 | 2016-06-27 14:49
| Improved UI | Submit button read as list | Make a Claim | DEF0003965 | Open | Attila | Gillian | Severity 2 | Priority 2 |  | 2016-06-20 09:43 | 2016-06-20 09:37 | 2016-06-23 10:57
| Improved UI | Email is not a required field | Make a Claim | DEF0004067 | Re-Open | Attila | Gillian | Severity 2 | Priority 2 |  | 2016-06-23 11:29 | 2016-06-23 11:07 | 2016-06-27 10:51
| Improved UI | Error messages are not read if user misses a required field | Make a Claim | DEF0004068 | Open | Attila | Gillian | Severity 2 | Priority 2 |  | 2016-06-23 11:33 | 2016-06-23 11:29 | 2016-06-24 14:30
| Improved UI | Buttons need to be more descriptive | Make a Payment | DEF0004079 | Open | Attila | Gillian | Severity 2 | Priority 2 |  | 2016-06-23 12:26 | 2016-06-23 12:20 | 2016-06-23 14:28
| Improved UI | Screen reader should start at the top of the page | Make a Claim | DEF0004083 | Re-Open | Attila | Gillian | Severity 2 | Priority 2 |  | 2016-06-23 13:47 | 2016-06-23 13:24 | 2016-06-27 12:57
| Improved UI | Fields with Examples are being read as prepopulated | Make a Claim | DEF0004089 | Pending Mgt Decision | Attila | Gillian | Severity 2 | Priority 2 |  | 2016-06-23 14:27 | 2016-06-23 14:14 | 2016-06-27 12:31
| Improved Sign Up/On | Not able to toggle check box using keyboard |  | DEF0004106 | Open | Attila | Kiran | Severity 2 | Priority 2 |  | 2016-06-25 07:11 | 2016-06-25 07:10 | 2016-06-27 08:21
| Improved UI | Policy Expiry date Field - Need to read format | Make a Payment | DEF0004112 | Open | Attila | Gillian | Severity 2 | Priority 2 |  | 2016-06-25 09:19 | 2016-06-25 09:17 | 2016-06-25 09:19
| Improved UI | Required fields are not indicated | Make a Payment | DEF0004113 | Open | Attila | Gillian | Severity 2 | Priority 2 |  | 2016-06-25 09:23 | 2016-06-25 09:21 | 2016-06-25 09:23
| Improved UI | Fields are being read with "auto complete" |  | DEF0004115 | Re-Open | Attila | Gillian | Severity 2 | Priority 2 |  | 2016-06-25 10:50 | 2016-06-25 10:49 | 2016-06-27 13:42
Assigned To: Claudiu (3)
| Improved UI | Drop down fields are selected twice. | Business | DEF0003412 | Open | Claudiu | Gillian | Severity 2 | Priority 2 |  | 2016-05-24 15:57 | 2016-05-24 15:53 | 2016-06-21 10:29
| Improved UI | Continue buttons do not work | Make a Payment | DEF0003445 | Monitor | Claudiu | Gillian | Severity 2 | Priority 2 |  | 2016-05-25 12:26 | 2016-05-25 11:47 | 2016-06-23 11:55
| Improved UI | Edit buttons do not work | Make a Payment | DEF0003447 | Open | Claudiu | Gillian | Severity 2 | Priority 2 |  | 2016-05-25 12:33 | 2016-05-25 12:28 | 2016-06-21 10:29
Assigned To: Devaraj (1)
| Improved Sign Up/On | cookie expiry message displayed if left ideal for few hours and login |  | DEF0004014 | Need More Information | Devaraj | Devaraj | Severity 2 | Priority 2 |  | 2016-06-21 13:58 | 2016-06-21 13:54 | 2016-06-25 19:40
Assigned To: Gillian (3)
| Improved UI | Table column title should be Limite not Montant as it is now | Farm | DEF0002168 | Monitor | Gillian | Sarah | Severity 2 | Priority 2 |  | 2016-04-19 12:06 | 2016-04-19 12:02 | 2016-06-02 09:45
| Improved UI | Financial Advisor is Incorrect | Business | DEF0002614 | Monitor | Gillian | Gillian | Severity 2 | Priority 2 |  | 2016-04-28 12:52 | 2016-04-28 12:46 | 2016-06-13 11:45
| Improved UI | When tabbing to field the whole form is read | Make a Claim | DEF0004038 | Pending Mgt Decision | Gillian | Gillian | Severity 2 | Priority 2 |  | 2016-06-22 14:43 | 2016-06-22 14:41 | 2016-06-27 15:52
Assigned To: Joseph (1)
| Improved Sign Up/On | Wrong Dialog box heading and possible content updated needed |  | DEF0003347 | Re-Open | Joseph | Kiran | Severity 2 | Priority 2 |  | 2016-05-19 13:54 | 2016-05-19 13:49 | 2016-06-27 16:41
Assigned To: Kiran (4)
| Improved Sign Up/On | Password rules not validating in Advisor setup |  | DEF0003513 | Need More Information | Kiran | Kiran | Severity 2 | Priority 2 |  | 2016-05-31 13:07 | 2016-05-31 13:04 | 2016-06-27 18:16
| Improved Sign Up/On | Login session not expired if page is not in opened state |  | DEF0003715 | Need More Information | Kiran | Kiran | Severity 2 | Priority 2 |  | 2016-06-07 12:44 | 2016-06-07 12:40 | 2016-06-24 21:40
| Improved Sign Up/On | Design discrepancies |  | DEF0003929 | Monitor | Kiran | Kiran | Severity 2 | Priority 2 |  | 2016-06-16 10:05 | 2016-06-16 10:00 | 2016-06-21 15:00
| Improved Sign Up/On | Technical error during 'Resend validation' |  | DEF0004099 | Monitor | Kiran | Kiran | Severity 2 | Priority 2 |  | 2016-06-24 09:25 | 2016-06-24 09:22 | 2016-06-24 10:30
Assigned To: Lisa (8)
| Improved UI | Building Description does not appear on UI for Coverages or Endorsements | Business | DEF0002657 | Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-04-29 08:52 | 2016-04-29 08:47 | 2016-06-08 10:58
| Improved UI | Equipment Endorsement Label Does Not Appear on UI | Business | DEF0002662 | Re-Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-04-29 10:15 | 2016-04-29 10:02 | 2016-06-15 10:46
| Improved UI | Fine Art Coverages Label Does Not Appear on UI | Business | DEF0002674 | Re-Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-04-29 12:01 | 2016-04-29 12:01 | 2016-05-05 15:37
| Improved UI | Sign Coverages Label Does Not Appear on UI | Business | DEF0002681 | Re-Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-04-29 13:07 | 2016-04-29 13:07 | 2016-05-05 15:41
| Improved UI | Contractors Equipment Label Does Not Appear on UI | Business | DEF0002683 | Re-Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-04-29 14:11 | 2016-04-29 14:11 | 2016-06-08 10:29
| Improved UI | Waiver of Subrogation (Landlord) Endorsement does not appear on UI | Business | DEF0002872 | Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-05-04 12:49 | 2016-05-04 12:46 | 2016-06-15 11:42
| Improved UI | Wrap Up Coverages Not Loaded | Business | DEF0002928 | Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-05-05 14:44 | 2016-05-05 14:44 | 2016-05-05 15:55
| Improved UI | Builder's Risk Coverage Names have not been loaded | Business | DEF0002930 | Open | Lisa | Gillian | Severity 2 | Priority 2 |  | 2016-05-05 14:47 | 2016-05-05 14:47 | 2016-05-05 15:56
Assigned To: Sarah (1)
| Improved UI | Missing My Financial Advisor Data | Farm | DEF0002099 | Monitor | Sarah | Sarah | Severity 2 | Priority 2 |  | 2016-04-18 12:50 | 2016-04-18 12:45 | 2016-05-25 14:30
Assigned To: Subra (1)
| Improved Sign Up/On | Policy does not display |  | DEF0003670 | Re-Open | Subra | Sue | Severity 2 | Priority 2 |  | 2016-06-06 12:46 | 2016-06-06 12:39 | 2016-06-14 09:41
Assigned To: Timothy (5)
| Improved Sign Up/On | Headrs does not look correct for all English emails |  | DEF0002160 | Re-Open | Timothy | Devaraj | Severity 2 | Priority 2 |  | 2016-04-19 11:07 | 2016-04-19 11:03 | 2016-06-23 14:36
| Improved Sign Up/On | Email Confirmation Missing graphic | Make a Payment | DEF0003317 | Open | Timothy | Sarah | Severity 2 | Priority 2 |  | 2016-05-18 14:41 | 2016-05-18 14:34 | 2016-06-20 15:53
| Improved Sign Up/On | Wrong error message displayed when user enter wrong password more than three times during email upd |  | DEF0004007 | Re-Open | Timothy | Kiran | Severity 2 | Priority 2 |  | 2016-06-21 11:08 | 2016-06-21 11:05 | 2016-06-27 16:33
| Improved Sign Up/On | Update password screen not throwing error when user use the passwrod from last four passwords |  | DEF0004013 | Re-Open | Timothy | Kiran | Severity 2 | Priority 2 |  | 2016-06-21 13:52 | 2016-06-21 13:48 | 2016-06-27 15:10
| Improved Sign Up/On | Should not allow to update password to one of the password from last four passwords |  | DEF0004086 | Re-Open | Timothy | Kiran | Severity 2 | Priority 2 |  | 2016-06-23 14:02 | 2016-06-23 13:57 | 2016-06-28 08:52
Assigned To: Vandy (5)
| Improved Sign Up/On | Wrong success message displayed when migrating user changed the email id. |  | DEF0003912 | Re-Open | Vandy | Kiran | Severity 2 | Priority 2 |  | 2016-06-15 11:21 | 2016-06-15 11:13 | 2016-06-27 16:23
| Improved Sign Up/On | In mobile devices Label displayed in two lines, looks little confusing |  | DEF0004064 | Re-Open | Vandy | Kiran | Severity 2 | Priority 2 |  | 2016-06-23 09:49 | 2016-06-23 09:47 | 2016-06-27 12:59
| Improved Sign Up/On | Wrong email subject line when user updated security answer. |  | DEF0004069 | Re-Open | Vandy | Kiran | Severity 2 | Priority 2 |  | 2016-06-23 11:36 | 2016-06-23 11:33 | 2016-06-27 12:52
| Improved Sign Up/On | Wrong email subject for the email received after password update. |  | DEF0004075 | Re-Open | Vandy | Kiran | Severity 2 | Priority 2 |  | 2016-06-23 12:03 | 2016-06-23 12:02 | 2016-06-27 13:13
| Improved Sign Up/On | Wrong sucess message after closing account |  | DEF0004107 | Re-Open | Vandy | Kiran | Severity 2 | Priority 2 |  | 2016-06-25 07:27 | 2016-06-25 07:25 | 2016-06-27 13:11